## Sheet1
Action | Owner | Details | Start date | Due date | Completed
Flooding | BH | Update | 2023-07-03 | 2024-06-03
Ditches | BH | See if the PC can claim reimbursement for ditches | 2023-07-03 | 2024-06-03
VH Review | CJ & SB | Review the running costs vs income for the village hall | 2023-09-04 | 2024-06-03
Westonfields | BH & GR | Broadband company road damage on Westonfields | 2024-01-08 | 2024-06-03
Bins | CJ | Clerk to look into bins for rec ground | 2024-01-08 | 2024-06-03
Bakery Mews | BH | Update | 2024-02-15 | 2024-06-03
Santa Fir | AM & CJ | Liaise with landowners and Countryside Access about clearing footpath | 2024-02-15 | 2024-06-03
Allotments | GR | To be sprayed, strimmed, and remarked | 2024-02-15 | 2024-06-03
Blackwell Farm | CJ & BH | Find out more information on the sale of Blackwell Farm by GBC | 2024-04-08 | 2024-06-03
New Road | BH | Update on the repair of New Road | 2024-04-08 | 2024-06-03
Church Lane | NE | Update on the clearing of the ditch at Church Lane | 2024-04-08 | 2024-06-03
ML Lights | NE | Quote for the replacement of the lights at the library to LED | 2024-04-08 | 2024-06-03
Defibrillators | CJ & NE | Replacement of defibs including turning FG phonebox into defib | 2024-04-08 | 2024-06-03
Rec ground | NE | Replacement of bark in the recreation ground | 2024-04-08 | 2024-06-03
VH heating | CJ & SB | Monitor the heating issues in village hall | 2024-04-08 | 2024-06-03
Allotments | GR | Chase the last outstanding allotment invoice | 2024-04-08 | 2024-06-03
Committees | CJ | Update new committees and working groups | 2024-05-13 | 2024-06-03
ML Clock | SB | Look into repair of memorial library clock | 2024-05-13 | 2024-06-03
Bridge | NE & BH | Look into repair of Sherbourne Bridge will steel crash barrier | 2024-05-13 | 2024-06-03
SUEZ/SITA | NE | Installation of SUEZ/SITA Viewpoint sign | 2024-05-13 | 2024-06-03
Westonfields | NE | Installation of slow down sign | 2024-05-13 | 2024-06-03
FG Tree | NE | Quotes for replacement of tree at Westonfields | 2024-05-13 | 2024-06-03
Westonfields | NE | Installation of equipment for younger children at the rec | 2024-05-13 | 2024-07-01