## Sheet1
Owner | Action | Details | Start date | Due date | Completed
BH | Flooding | Update | 2023-07-03 | 2024-09-02
CJ & SB | VH Review | Review the running costs vs income for the village hall | 2023-09-04 | 2024-07-01
BH & GR | Westonfields | Broadband company road damage on Westonfields | 2024-01-08 | 2024-09-02
CJ | Bins | Clerk to look into bins for rec ground | 2024-01-08 | 2024-07-01
BH | Bakery Mews | Update | 2024-02-15 | 2024-07-01
AM & CJ | Santa Fir | Liaise with landowners and Countryside Access about clearing footpath | 2024-02-15 | 2024-07-01
GR | Allotments | To be sprayed, strimmed, and remarked | 2024-02-15 | 2024-09-02
BH | New Road | Update on the repair of New Road | 2024-04-08 | 2024-07-01
NE | Church Lane | Update on the clearing of the ditch at Church Lane | 2024-04-08 | 2024-07-01
NE | ML Lights | Quote for the replacement of the lights at the library to LED | 2024-04-08 | 2024-07-01
CJ & NE | Defibrillators | Replacement of defibs including turning FG phonebox into defib | 2024-04-08 | 2024-07-01
NE | Rec ground | Replacement of bark in the recreation ground | 2024-04-08 | 2024-07-01
CJ & SB | VH heating | Monitor the heating issues in village hall | 2024-04-08 | 2024-10-07
GR | Allotments | Chase the last outstanding allotment invoice | 2024-04-08 | 2024-09-02
SB | ML Clock | Look into repair of memorial library clock | 2024-05-13 | 2024-07-01
NE & BH | Bridge | Look into repair of Sherbourne Bridge will steel crash barrier | 2024-05-13 | 2024-07-01
NE | FG Tree | Planting of tree on Farley Green | 2024-05-13 | 2024-07-01
NE | Westonfields | Installation of equipment for younger children at the rec | 2024-05-13 | 2024-09-02
NE | SUEZ/SITA sign | Improvement of installation of sign at Viewing Platform | 2024-06-03 | 2024-07-01
CJ | s106 | S106 monies for defibrillators | 2024-06-03 | 2024-07-01
BH | Westonfields | Look into funding for play equipment for younger children | 2024-06-03 | 2024-07-01