## Sheet1
Owner | Action | Details | Start date | Due date | Completed
BH | Flooding | Update | 2023-07-03 | 2024-10-07
BH & GR | Westonfields | Broadband company road damage on Westonfields | 2024-01-08 | 2024-10-07
BH | Bakery Mews | Update | 2024-02-15 | 2024-12-02
AM & CJ | Santa Fir | Liaise with landowners and Countryside Access about clearing footpath | 2024-02-15 | 2024-10-07
GR | Allotments | To be sprayed, strimmed, and remarked | 2024-02-15 | 2024-10-07
BH | New Road | Update on the repair of New Road | 2024-04-08 | 2024-11-04
NE | Rec ground | Replacement of bark in the recreation ground | 2024-04-08 | 2024-10-07
CJ & SB | VH heating | Monitor the heating issues in village hall | 2024-04-08 | 2024-10-07
GR | Allotments | Chase the last outstanding allotment invoice | 2024-04-08 | 2024-10-07
SB | ML Clock | Look into repair of memorial library clock | 2024-05-13 | 2024-10-07
NE & BH | Bridge | Look into repair of Sherbourne Bridge will steel crash barrier | 2024-05-13 | 2024-10-07
AM | Westonfields | Quotes for equipment for younger children at the rec | 2024-05-13 | 2024-10-07
BH | Westonfields | Look into funding for play equipment for younger children | 2024-06-03 | 2024-10-07
NE | Ditch clearing | Discuss with Estate about regularly clearing the ditch | 2024-09-02 | 2024-11-04
CJ | Bins | Discuss replacement of bins with manufacturer | 2024-09-02 | 2024-10-07
NE | Strimming | Request contractor strims footpaths | 2024-09-02 | 2024-10-07
BH | Waste clearing | Chase the clearing of the waste on New Road and Sherbourne Road | 2024-10-07 | 2024-10-07
BH | Highways | Find out whether mirror can be put at Guildford Ln/Chilworth Rd | 2024-10-07 | 2024-11-04
SB | Churches | Invite rector of the beneficiary to a meeting | 2024-10-07 | 2024-11-04
NE | Troughs | Look into planting in other troughs in the village | 2024-10-07 | 2024-11-04