## Current
ACTION ITEMS
ALBURY PARISH COUNCIL		Last updated:	02/09/25

	Action	Details	Start date	Due date	Completed	Minute ref	Status	Notes

AM	Churches	Update on maintenance funds to the church	04/11/24	12/01/25		028/24	25%
BH	Flooding	Update on installation of new drains at Westonfields	03/07/23	12/01/25		036/24	25%
SB	ML Clock	Look into repair of memorial library clock	13/05/24	12/01/25		147/24	50%
SB	Traffic calming	Look into more secure VAS options	17/02/25	12/01/25		026/25	0%
SB	Village Hall	Replace purchased chair feet	17/02/25	12/01/25		032/25	50%
AM & BH	Network Rail	Chasing repairs from damage caused by diversions and to level crossing	07/04/25	12/01/25		057/25	50%
CJ	Village Hall	Confirm funding of village hall sign from Albury Estate	07/04/25	12/01/25		062/25	25%

## Archive
COMPLETED ITEMS
ALBURY PARISH COUNCIL					Last updated:	1/21/2025

	Action	Details	Start date	Due date	Completed	Minute ref	Status	Done?	Notes

CJ	Allotments	Update allotment regulations and conduct price review	07/10/24	03/02/25	1/7/2025	166/24	100%			Yes
CJ	Accounts	Organise back payment	04/11/24	23/11/24	11/23/2024		100%			Yes
SB	Bin emptying	Inform Cricket Club that Council will not be contributing to costs	04/11/24	18/11/24	11/18/2024		100%			Yes
BH	Waste clearing	Chase the clearing of the waste on New Road and Sherbourne Road	07/10/24	02/12/24	11/4/2024	166/24	0%	No responsibility taken - item closed		No
SB	Highways	Find out whether mirror can be put at Guildford Ln/Chilworth Rd	07/10/24	06/01/25	1/6/2025	166/24	0%	Request Rejected		No
BH	Footpaths	Update on regular footpath clearing at Boundary Cottages	04/11/24	06/01/25	1/6/2025		0%	Cleared		No
NE & BH	Bridge	Look into repair of Sherbourne Bridge	13/05/24	03/02/25	2/3/2025	100/24	100%			Yes
BH	Westonfields	Broadband company road damage on Westonfields	08/01/24	03/02/25	2/3/2025	006/24	100%			Yes
NE	Rec ground	Organise replacement of bark in the recreation ground	04/11/24	03/02/25	1/25/2025	076/24	100%			Yes
AM & NE	Rec ground	Organise replacement of play equipment for younger children	04/11/24	03/02/25	1/25/2025	100/24	100%			Yes
CJ	Grants	Look into funding for the church maintenance	02/12/24	03/03/25	3/3/2025	075/24	0%	None available		No
CJ	APM	Annual Parish Meeting prep - invites and advertising	17/02/25	30/04/25	1/4/2025	184/24	100%			Yes
CJ	Allotments	Look into options for strimming and clearing just a few plots	15/02/24	07/04/25	4/3/2025	096/24	100%			Yes
NE	Farley Green	Discuss knotweed removal with contractors	17/02/25	07/04/25	3/3/2025	026/25	100%			Yes
SB	Village Hall	Amendments to VH and ML lease	17/02/25	03/03/25	3/3/2025	032/25	100%			Yes
BH	New Road	Update on the repair of New Road	08/04/24	12/05/25		143/23	100%	Not possible		Yes
NE	Troughs	Organise planting of troughs	02/09/24	12/05/25		154/24	0%	No budget		No
CJ	Traffic calming	Look into obtaining data from speed cameras	17/02/25	02/06/25		026/25	0%	Not possible		No
NE & AM	Flooding	Update on final agreement for the pipe replacement at Farley Green	02/09/24	12/01/25		026/25	100%	Work completed
BH	Business rates	Confirmation of any reductions available for business rates	02/09/25	12/01/25			100%	No reduction possible
BH	Bakery Mews	Date confirmation for kerb build out	15/02/24	12/01/25		028/25	100%