## Current
ACTION ITEMS
ALBURY PARISH COUNCIL		Last updated:	11/05/2026

	Action	Details	Start date	Due date	Completed	Minute ref	Status	Notes

BH	Flooding	Update on installation of new drains at Westonfields	03/07/2023	11/05/2026		036/24	25%
SB	ML Clock	Look into repair of memorial library clock	13/05/2024	11/05/2026		147/24	50%
SB	Traffic calming	Look into more secure VAS options	17/02/2025	11/05/2026		026/25	0%
AM & BH	Network Rail	Chasing repairs from damage caused by diversions and to level crossing	07/04/2025	11/05/2026		057/25	50%
AM & SB	Church	Review finances for church maintenance contribution	02/03/26	11/05/26		038/26 (c)	25%
AM & SB	Policies	Review complaints procedure	12/05/26	01/06/26		062/26	0%
SB	Policies	Draft a data retention policy	12/05/26	01/06/26		063/26	0%
CJ	Insurance	Prepare insurance review for September	12/05/26	01/09/26		060/26	0%
CJ	Maintenance	Draft a letter for waste left at Westonfields	12/05/26	01/06/26		070/26 (c)	50%
CJ	Maintenance	Draft a letter regarding the repair of the wall at Millennium Cottages	12/05/26	01/06/26		070/26 (h)	100%

## Archive
COMPLETED ITEMS
ALBURY PARISH COUNCIL					Last updated:	21/01/2025

	Action	Details	Start date	Due date	Completed	Minute ref	Status	Done?	Notes

CJ	Allotments	Update allotment regulations and conduct price review	07/10/2024	03/02/2025	07/01/2025	166/24	100%			Yes
CJ	Accounts	Organise back payment	04/11/2024	23/11/2024	23/11/2024		100%			Yes
SB	Bin emptying	Inform Cricket Club that Council will not be contributing to costs	04/11/2024	18/11/2024	18/11/2024		100%			Yes
BH	Waste clearing	Chase the clearing of the waste on New Road and Sherbourne Road	07/10/2024	02/12/2024	04/11/2024	166/24	0%	No responsibility taken - item closed		No
SB	Highways	Find out whether mirror can be put at Guildford Ln/Chilworth Rd	07/10/2024	06/01/2025	06/01/2025	166/24	0%	Request Rejected		No
BH	Footpaths	Update on regular footpath clearing at Boundary Cottages	04/11/2024	06/01/2025	06/01/2025		0%	Cleared		No
NE & BH	Bridge	Look into repair of Sherbourne Bridge	13/05/2024	03/02/2025	03/02/2025	100/24	100%			Yes
BH	Westonfields	Broadband company road damage on Westonfields	08/01/2024	03/02/2025	03/02/2025	006/24	100%			Yes
NE	Rec ground	Organise replacement of bark in the recreation ground	04/11/2024	03/02/2025	25/01/2025	076/24	100%			Yes
AM & NE	Rec ground	Organise replacement of play equipment for younger children	04/11/2024	03/02/2025	25/01/2025	100/24	100%			Yes
CJ	Grants	Look into funding for the church maintenance	02/12/2024	03/03/2025	03/03/2025	075/24	0%	None available		No
CJ	APM	Annual Parish Meeting prep - invites and advertising	17/02/2025	30/04/2025	04/01/2025	184/24	100%			Yes
CJ	Allotments	Look into options for strimming and clearing just a few plots	15/02/2024	07/04/2025	03/04/2025	096/24	100%			Yes
NE	Farley Green	Discuss knotweed removal with contractors	17/02/2025	07/04/2025	03/03/2025	026/25	100%			Yes
SB	Village Hall	Amendments to VH and ML lease	17/02/2025	03/03/2025	03/03/2025	032/25	100%			Yes
BH	New Road	Update on the repair of New Road	08/04/2024	12/05/2025		143/23	100%	Not possible		Yes
NE	Troughs	Organise planting of troughs	02/09/2024	12/05/2025		154/24	0%	No budget		No
CJ	Traffic calming	Look into obtaining data from speed cameras	17/02/2025	02/06/2025		026/25	0%	Not possible		No
NE & AM	Flooding	Update on final agreement for the pipe replacement at Farley Green	02/09/2024	12/01/2025		026/25	100%	Work completed
BH	Business rates	Confirmation of any reductions available for business rates	02/09/2025	12/01/2025			100%	No reduction possible
BH	Bakery Mews	Date confirmation for kerb build out	15/02/2024	12/01/2025		028/25	100%
AM	Churches	Update on maintenance funds to the church	04/11/2024	12/01/2025	12-Jan	028/24	100%
CJ	Village Hall	Confirm funding of village hall sign from Bob Hughes	07/04/2025	11/05/2026		062/25	100%
SB	Village Hall	Replace purchased chair feet	17/02/2025	11/05/2026	02/03/26	032/25	100%