## Sheet1
ACTION ITEMS
ALBURY PARISH COUNCIL |  | Last updated: | 2024-11-04
BH | Action | Details | Start date | Due date | Completed | Minute ref | Status | Done? | Notes
NE | Troughs | Look into planting in other troughs in the village | 2024-09-02 | 2024-04-01 |  | 154/24 | 0% | N
CJ | Allotments | Update allotment regulations and conduct price review | 2024-10-07 | 2025-01-06 |  | 166/24 | 0% | N
SB | Churches | Update on the churches | 2024-11-04 | 2025-01-06 |  | 184/24 | 0% | N
CJ | Grants | Look into funding for the church maintenance | 2024-12-02 | 2025-01-06 |  |  | 0% | N
BH | Flooding | Update | 2023-07-03 | 2025-01-06 |  | 143/23 | 25% | N
BH | Footpaths | Update on regular footpath clearing at Boundary Cottages | 2024-11-04 | 2025-01-06 |  |  | 25% | N
GR | Allotments | Organise strimming and clearing of allotments | 2024-02-15 | 2025-01-06 |  | 036/24 | 50% | N
SB | ML Clock | Look into repair of memorial library clock | 2024-05-13 | 2025-01-06 |  | 096/24 | 50% | N
BH | Westonfields | Broadband company road damage on Westonfields | 2024-01-08 | 2025-01-06 |  | 006/24 | 75% | N
BH | Bakery Mews | Update on kerb build out | 2024-02-15 | 2025-01-06 |  | 028/24 | 75% | N
BH | New Road | Update on the repair of New Road | 2024-04-08 | 2025-01-06 |  | 075/24 | 75% | N
NE | Rec ground | Organise replacement of bark in the recreation ground | 2024-11-04 | 2025-01-06 |  | 076/24 | 75% | N
NE & BH | Bridge | Look into repair of Sherbourne Bridge | 2024-05-13 | 2025-01-06 |  | 100/24 | 75% | N
AM & NE | Rec ground | Organise replacement of play equipment for younger children | 2024-11-04 | 2025-01-06 |  | 100/24 | 75% | N
NE | Ditch clearing | Discuss with Estate about regularly clearing the ditch | 2024-09-02 | 2025-01-06 |  | 147/24 | 75% | N | No responsibility taken - item closed
SB | Highways | Find out whether mirror can be put at Guildford Ln/Chilworth Rd | 2024-10-07 | 2025-01-06 |  | 166/24 | 75% | N
CJ | Accounts | Organise back payment | 2024-11-04 | 2024-11-23 | 2024-11-23 |  | 100% | N
SB | Bin emptying | Inform Cricket Club that Council will not be contributing to costs | 2024-11-04 | 2024-11-18 | 2024-11-18 |  | 100% | Y
BH | Waste clearing | Chase the clearing of the waste on New Road and Sherbourne Road | 2024-10-07 | 2024-12-02 | 2024-11-04 | 166/24 | 100% | Y