## Current
ACTION ITEMS
ALBURY PARISH COUNCIL |  | Last updated: | 24/2/25
| Action | Details | Start date | Due date | Completed | Minute ref | Status | Notes | Archive
NE | Troughs | Look into planting in other troughs in the village - artificial flowers | 2024-09-02 | 2025-07-04 |  | 154/24 | 0% |  | No
AM | Churches | Update on maintenance funds to the church | 2024-11-04 | 2025-03-03 |  | 028/24 | 0% |  | No
CJ | Grants | Look into funding for the church maintenance | 2024-12-02 | 2025-03-03 |  | 075/24 | 0% |  | No
BH | Flooding | Update | 2023-07-03 | 2025-03-03 |  | 036/24 | 25% |  | No
GR | Allotments | Look into options for strimming and clearing just a few plots | 2024-02-15 | 2025-03-03 |  | 096/24 | 0% |  | No
SB | ML Clock | Look into repair of memorial library clock | 2024-05-13 | 2025-05-12 |  | 147/24 | 50% |  | No
BH | Bakery Mews | Date confirmation for kerb build out | 2024-02-15 | 2025-03-03 |  | 028/25 | 75% |  | No
BH | New Road | Update on the repair of New Road | 2024-04-08 | 2025-03-03 |  | 143/23 | 75% |  | No
NE & AM | Ditch clearing | Update on agreement about ongoing ditch maintenance | 2024-09-02 | 2025-02-19 |  | 026/25 | 50% |  | No
CJ | APM | Annual Parish Meeting prep - invites and advertising | 2025-02-17 | 2025-04-30 |  | 184/24 | 25% |  | No
CJ | Traffic calming | Look into obtaining data from speed cameras | 2025-02-17 | 2025-03-03 |  |  | 0% |  | No
CJ | Traffic calming | Look into options for average speed cameras in the parish | 2025-02-17 | 2025-03-03 |  | 026/25 | 0% |  | No
SB | Traffic calming | Look into more secure VAS options | 2025-02-17 | 2025-03-03 |  | 026/25 | 0% |  | No
NE | Farley Green | Discuss knotweed removal with contractors | 2025-02-17 | 2025-03-03 |  | 026/25 | 50% |  | No
SB | Village Hall | Amendments to VH and ML lease | 2025-02-17 | 2025-07-04 |  | 032/25 | 0% |  | No
SB | Village Hall | Replacement of feet of chairs | 2025-02-17 | 2025-05-12 |  | 032/25 | 0% |  | No

## Archive
COMPLETED ITEMS
ALBURY PARISH COUNCIL | [6 empty] | Last updated: | 2025-01-21
| Action | Details | Start date | Due date | Completed | Minute ref | Status | Done? | Notes
CJ | Allotments | Update allotment regulations and conduct price review | 2024-10-07 | 2025-02-03 | 2025-01-07 | 166/24 | 100% |  |  | Yes
CJ | Accounts | Organise back payment | 2024-11-04 | 2024-11-23 | 2024-11-23 |  | 100% |  |  | Yes
SB | Bin emptying | Inform Cricket Club that Council will not be contributing to costs | 2024-11-04 | 2024-11-18 | 2024-11-18 |  | 100% |  |  | Yes
BH | Waste clearing | Chase the clearing of the waste on New Road and Sherbourne Road | 2024-10-07 | 2024-12-02 | 2024-11-04 | 166/24 | 100% | No responsibility taken - item closed |  | Yes
SB | Highways | Find out whether mirror can be put at Guildford Ln/Chilworth Rd | 2024-10-07 | 2025-01-06 | 2025-01-06 | 166/24 | 100% | Request Rejected |  | Yes
BH | Footpaths | Update on regular footpath clearing at Boundary Cottages | 2024-11-04 | 2025-01-06 | 2025-01-06 |  | 100% | Cleared |  | Yes
NE & BH | Bridge | Look into repair of Sherbourne Bridge | 2024-05-13 | 2025-02-03 | 2025-02-03 | 100/24 | 100% |  |  | Yes
BH | Westonfields | Broadband company road damage on Westonfields | 2024-01-08 | 2025-02-03 | 2025-02-03 | 006/24 | 100% |  |  | Yes
NE | Rec ground | Organise replacement of bark in the recreation ground | 2024-11-04 | 2025-02-03 | 2025-01-25 | 076/24 | 100% |  |  | Yes
AM & NE | Rec ground | Organise replacement of play equipment for younger children | 2024-11-04 | 2025-02-03 | 2025-01-25 | 100/24 | 100% |  |  | Yes