## Current
ACTION ITEMS
ALBURY PARISH COUNCIL |  | Last updated: | 2025-02-06
| Action | Details | Start date | Due date | Completed | Minute ref | Status | Notes
AM | Churches | Update on maintenance funds to the church | 2024-11-04 | 2025-07-07 |  | 028/24 | 25%
BH | Flooding | Update on installation of new drains at Westonfields | 2023-07-03 | 2025-07-07 |  | 036/24 | 25%
SB | ML Clock | Look into repair of memorial library clock | 2024-05-13 | 2025-07-07 |  | 147/24 | 50%
BH | Bakery Mews | Date confirmation for kerb build out | 2024-02-15 | 2025-07-07 |  | 028/25 | 75%
NE & AM | Flooding | Update on final agreement for the pipe replacement at Farley Green | 2024-09-02 | 2025-07-07 |  | 026/25 | 50%
CJ | Traffic calming | Look into options for average speed cameras in the parish | 2025-02-17 | 2025-07-07 |  | 026/25 | 25%
SB | Traffic calming | Look into more secure VAS options | 2025-02-17 | 2025-07-07 |  | 026/25 | 0%
SB | Village Hall | Replacement of feet of chairs | 2025-02-17 | 2025-07-07 |  | 032/25 | 0%
AM & BH | Network Rail | Chasing repairs from damage caused by diversions and to level crossing | 2025-04-07 | 2025-10-06 |  | 057/25 | 25%
NE | Village Hall | Confirm funding of village hall sign from Albury Estate | 2025-04-07 | 2025-07-07 |  | 062/25 | 25%
CJ | Framing | Village Hall Jubilee picture framing | 2024-05-01 | 2025-07-07 |  |  | 50%

## Archive
COMPLETED ITEMS
ALBURY PARISH COUNCIL | [6 empty] | Last updated: | 2025-01-21
| Action | Details | Start date | Due date | Completed | Minute ref | Status | Done? | Notes
CJ | Allotments | Update allotment regulations and conduct price review | 2024-10-07 | 2025-02-03 | 2025-01-07 | 166/24 | 100% |  |  | Yes
CJ | Accounts | Organise back payment | 2024-11-04 | 2024-11-23 | 2024-11-23 |  | 100% |  |  | Yes
SB | Bin emptying | Inform Cricket Club that Council will not be contributing to costs | 2024-11-04 | 2024-11-18 | 2024-11-18 |  | 100% |  |  | Yes
BH | Waste clearing | Chase the clearing of the waste on New Road and Sherbourne Road | 2024-10-07 | 2024-12-02 | 2024-11-04 | 166/24 | 0% | No responsibility taken - item closed |  | No
SB | Highways | Find out whether mirror can be put at Guildford Ln/Chilworth Rd | 2024-10-07 | 2025-01-06 | 2025-01-06 | 166/24 | 0% | Request Rejected |  | No
BH | Footpaths | Update on regular footpath clearing at Boundary Cottages | 2024-11-04 | 2025-01-06 | 2025-01-06 |  | 0% | Cleared |  | No
NE & BH | Bridge | Look into repair of Sherbourne Bridge | 2024-05-13 | 2025-02-03 | 2025-02-03 | 100/24 | 100% |  |  | Yes
BH | Westonfields | Broadband company road damage on Westonfields | 2024-01-08 | 2025-02-03 | 2025-02-03 | 006/24 | 100% |  |  | Yes
NE | Rec ground | Organise replacement of bark in the recreation ground | 2024-11-04 | 2025-02-03 | 2025-01-25 | 076/24 | 100% |  |  | Yes
AM & NE | Rec ground | Organise replacement of play equipment for younger children | 2024-11-04 | 2025-02-03 | 2025-01-25 | 100/24 | 100% |  |  | Yes
CJ | Grants | Look into funding for the church maintenance | 2024-12-02 | 2025-03-03 | 2025-03-03 | 075/24 | 0% | None available |  | No
CJ | APM | Annual Parish Meeting prep - invites and advertising | 2025-02-17 | 2025-04-30 | 2025-01-04 | 184/24 | 100% |  |  | Yes
CJ | Allotments | Look into options for strimming and clearing just a few plots | 2024-02-15 | 2025-04-07 | 2025-04-03 | 096/24 | 100% |  |  | Yes
NE | Farley Green | Discuss knotweed removal with contractors | 2025-02-17 | 2025-04-07 | 2025-03-03 | 026/25 | 100% |  |  | Yes
SB | Village Hall | Amendments to VH and ML lease | 2025-02-17 | 2025-03-03 | 2025-03-03 | 032/25 | 100% |  |  | Yes
BH | New Road | Update on the repair of New Road | 2024-04-08 | 2025-05-12 |  | 143/23 | 100% | Not possible |  | Yes
NE | Troughs | Organise planting of troughs | 2024-09-02 | 2025-05-12 |  | 154/24 | 0% | No budget |  | No
CJ | Traffic calming | Look into obtaining data from speed cameras | 2025-02-17 | 2025-06-02 |  | 026/25 | 0% | Not possible |  | No